## project management data
Project Name | Task Name | Assigned To | Start Date | Days Required | End Date | Progress | Cost
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 38% | 1741089
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 25% | 230071
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0% | 1148912
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78% | 191708
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0% | 1757908
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 20% | 1209282
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 60% | 1581662
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0% | 376043
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10% | 1978299
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78% | 914785
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50% | 1257231
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0% | 407874
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0% | 589765
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100% | 485286
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0% | 467422
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0% | 1838220
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30% | 1958181
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0% | 1370705
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0% | 1683109
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 30% | 564927
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 25% | 239424
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0% | 774500
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100% | 1096869
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100% | 1862557
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0% | 1437017
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40% | 1848717
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0% | 1933018
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0% | 1987908
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60% | 1264058
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0% | 1750150
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0% | 1495289
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80% | 391699
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0% | 877778
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0% | 1366272
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30% | 1766994
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0% | 1718743
Events | Sponsorship Coordinatio | Nancy | 2024-02-24 | 35 | 2024-03-30 | 0% | 538621
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50% | 184900
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 40% | 1598219
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0% | 969025
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20% | 1988680
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0% | 1520170
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0% | 756093

## Sorting
Project Name | Sum of Cost
Operations | 5769643
Production | 5011995
Consulting | 4509497
Support | 4396443
Engineering | 4264943
Events | 4024358
Customer Svc | 3166987
Marketing | 3120072
Financial | 2893084
Development | 2790928
Logistics | 2752144
Training | 2635749
Research | 2254870
Product Dev | 1949616
Sales | 1578851
Grand Total | 51119180
o

## Filtering
Progress | (Multiple Items)
Sum of Progress | Project Name
Assigned To | Consulting | Customer Svc | Development | Financial | Product Dev | Support | Training | Grand Total
Aaron | [5 empty] | 1 |  | 1
Fiona | 0.6 |  |  |  | 0.78 |  |  | 1.38
Ian |  | 0.6 | [5 empty] | 0.6
Isaac | [6 empty] | 0.8 | 0.8
Mark |  |  |  | 0.78 |  |  |  | 0.78
Quinn |  |  | 1 |  |  |  |  | 1
Zoe | [5 empty] | 1 |  | 1
Grand Total | 0.6 | 0.6 | 1 | 0.78 | 0.78 | 2 | 0.8 | 6.56

## TRY IT
Progress | 100%
Task Name | Sum of Progress
Bug Fixes | 1
Software Development | 1
Technical Support | 1
Grand Total | 3

## pivot chart
Sum of Days Required | Project Name
Start Date | Development | Sales | Grand Total
2024-01-06 |  | 20 | 20
2024-03-14 | 30 |  | 30
2024-02-08 | 34 |  | 34
2024-02-03 |  | 35 | 35
2024-01-02 | 36 |  | 36
2024-01-03 |  | 60 | 60
Grand Total | 100 | 115 | 215

## Sheet1
Sum of Days Required | Project Name
Start Date | Development | Sales | Grand Total
2024-01-06 |  | 20 | 20
2024-03-14 | 30 |  | 30
2024-02-08 | 34 |  | 34
2024-02-03 |  | 35 | 35
2024-01-02 | 36 |  | 36
2024-01-03 |  | 60 | 60
Grand Total | 100 | 115 | 215